## Sheet1
Project Plan
CS 6440 - Team Radio Star
Legend | PM | Dev | QA | Design | Full Team
Week of | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28
Team formation
Topic video
Status updates and communication with faculty & Dr. Oiyemhonlan
Project plan
Initial UI mockups
Requirements
Research and determine data sources
Architecture & implementation plan
|  |  | User stories | Final UI hi-fis
Assist dev and QA squads as needed
Technical presentation
Main app and data service development
Produce UI assets
Create test plan
Initial app testing
Feedback from Dr. Oiyemhonlan
Progress report
Bug fixes and enhancements
Testing and fix verification
User feedback
Final presentation